## 역할별 작업분해표
WBS ID | 단계 | 역할 | 작업명 | 입력 | 출력 | 완료 기준 | 의존성 | 우선순위 | 증거 | 병렬성 | 책임
WBS-001 | governance | ceo | Set objective, priorities, and final decision criteria. | work-design | decision criteria | decision criteria exists and can satisfy design review completed; qa qc review completed; final decision gate completed | work-design | high | work-design | sequential dependency stage | define success; resolve priority conflicts
WBS-002 | governance | advisor | Challenge assumptions and surface missing perspectives. | work-design | advisory notes | advisory notes exists and can satisfy design review completed; qa qc review completed; final decision gate completed | work-design | high | work-design | sequential dependency stage | identify blind spots; suggest alternatives
WBS-003 | design | domain-designer | Create mandatory work design and required artifact list. |  | work-design; role-task-plan; evidence-plan; risk-policy-checklist | work-design; role-task-plan; evidence-plan; risk-policy-checklist exists and can satisfy design review completed; qa qc review completed; final decision gate completed | work-design | high | work-design; role-task-plan; evidence-plan; risk-policy-checklist | sequential dependency stage | classify domain; define subdomains; define artifacts
WBS-004 | planning | decomposition-planner | Split the work into bounded role tasks. | work-design; role-task-plan | task plan | task plan exists and can satisfy design review completed; qa qc review completed; final decision gate completed | work-design; role-task-plan | high | work-design; role-task-plan | sequential dependency stage | map artifacts to tasks; sequence review gates
WBS-005 | execution | specialist | Execute assigned domain-specific work. | work-design; role-task-plan | specialist result | specialist result exists and can satisfy design review completed; qa qc review completed; final decision gate completed | work-design; role-task-plan | normal | work-design; role-task-plan | parallel when inputs are independent | produce assigned deliverables; record evidence
WBS-006 | review | reviewer | Review outputs against the design artifacts. | work-design; evidence-plan | review findings | review findings exists and can satisfy design review completed; qa qc review completed; final decision gate completed | work-design; evidence-plan | high | work design saved; artifact manifest saved; required design artifacts saved; risk policy checked; design review completed; qa qc review completed; final decision gate completed | parallel when inputs are independent | find contradictions; find missing requirements
WBS-007 | qa | qa-qc-verifier | Verify quality, completeness, and evidence coverage. | evidence-plan | qa qc result | qa qc result exists and can satisfy design review completed; qa qc review completed; final decision gate completed | evidence-plan | high | work design saved; artifact manifest saved; required design artifacts saved; risk policy checked; design review completed; qa qc review completed; final decision gate completed | parallel after review fan-in | check deliverables; check evidence
WBS-008 | risk | risk-policy-reviewer | Check safety, risk, policy, and sensitive information concerns. | risk-policy-checklist | risk policy result | risk policy result exists and can satisfy design review completed; qa qc review completed; final decision gate completed | risk-policy-checklist | high | work design saved; artifact manifest saved; required design artifacts saved; risk policy checked; design review completed; qa qc review completed; final decision gate completed | parallel after review fan-in | check risks; check sensitive data; check policy constraints
WBS-009 | final | final-decision-manager | Decide whether the workflow is complete or blocked. | work-design; role-task-plan; evidence-plan; risk-policy-checklist | final decision | final decision exists and can satisfy design review completed; qa qc review completed; final decision gate completed | work-design; role-task-plan; evidence-plan; risk-policy-checklist | high | work design saved; artifact manifest saved; required design artifacts saved; risk policy checked; design review completed; qa qc review completed; final decision gate completed | sequential dependency stage | inspect evidence; approve final output or request iteration
WBS-010 | execution | implementer | Produce requested target deliverable 10. | work-design; role-task-plan; source request | README.md | target deliverable exists, is reviewable, and has implementation evidence | work-design; role-task-plan | high | generated code written; implementation evidence recorded | parallel with other independent targets | execute assigned output; record evidence; surface blockers
WBS-011 | execution | implementer | Produce requested target deliverable 11. | work-design; role-task-plan; source request | src/app.py | target deliverable exists, is reviewable, and has implementation evidence | work-design; role-task-plan | high | generated code written; implementation evidence recorded | parallel with other independent targets | execute assigned output; record evidence; surface blockers